## Slide 1
Mini-SPOT: where we are now
Project status update · 5 phases · now moving into Phase 4
thws
Aditya Srivatsa
01
Research &
Planning
May 1 – Jul 30
complete
02
Hardware
Dev
Sep 16 – Oct 30
in progress
03
Software
& Sim
Sep 1 – Nov 15
in progress
04
Integration
& Testing
Nov 16 – Dec 31
WE ARE HERE
05
Finalization
Jan 1 – Jan 30
upcoming
6
tasks done
7
in progress
8
not started
+6
new results not yet on the board
Counts from our Miro Kanban board · “new results” = simulation work shown on slide 3
Notes: Our project has five phases. Research and planning is complete. Hardware and software and simulation are running in parallel, and we are now moving into phase four, integration and testing. On the Kanban board we have 6 tasks done, 7 in progress, 8 still to start - plus some new results from the last weeks that are not on the board yet, which I will show now.

## Slide 2
How far we came
Phases 1 – 3: what is finished and what is running
thws
Aditya Srivatsa
1
Completed
Research on architecture & final choice
All
Done
Parts research for Mini-SPOT
All
Done
MuJoCo simulation setup
All
Done
Arduino hard-coded walking & movement
All
Done
Milestone 1 presentation
All
Done
2
In progress
Head CAD finalization
Harsh · Bhavishya · Sravan
In progress
Jetson Nano setup & camera
Harsh · Bhavishya · Sravan
In progress
Sim-to-real transfer prep
Aditya · Thejasvi
In progress
Writing firmware
Harsh · Bhavishya · Sravan
In progress
Soldering new components
In progress
Integrating the head (LED)
In progress
Architecture & responsibility PPT
Bhavishya · Sravan · Harsh
In progress
Notes: On the left is everything that is finished: the research and parts selection, the MuJoCo simulation, a first hard-coded walk on the Arduino, and milestone one. On the right is what is running now: the head CAD, Jetson Nano and camera, firmware and soldering on the hardware side, and sim-to-real preparation on the software side.

## Slide 3
New: walking and steering in simulation
Part of Phase 3 · “Sim-to-real prep” and “Perfecting spot movements”
thws
Aditya Srivatsa
3
What we built
Smooth Bézier gait for all 4 legs
every leg follows a smooth curve, 50× per second
New · done
Walk and trot on command
one leg at a time, or diagonal pairs
New · done
Turn left / right by any angle
rotates on the spot, stops at the requested angle
New · done
Walk in a circle (left / right)
chosen radius, from 0.6 m upwards
New · done
RL training pipeline running
PPO tunes the 6 gait numbers · training crash fixed
New · done
Automated tests
5 checks for turning and circles, all passing
New · done
Measured in simulation
±2.5°
turn accuracy
30°, 90°, 180° · both directions
< 20 cm
drift while turning
turns on the spot
1.00 m
circle when asked for 1 m
2 m → 1.96–1.99 m
Notes: This is new and not on the Miro board yet. In simulation the robot now walks and trots with a smooth Bezier gait, turns left or right by any angle we type in, and walks circles of a chosen size. The turn lands within about two and a half degrees, and a 1 metre circle comes out at 1.00 metre. The reinforcement learning pipeline that tunes the gait is set up and running, and automated tests check the turning on every change.

## Slide 4
Phase 4: Integration & Testing
Nov 16 – Dec 31 · bringing simulation and hardware together
thws
Aditya Srivatsa
4
Phase 4 tasks
Jetson Nano & camera integration + testing
Nov 16–30 · Harsh · Bhavishya · Sravan
In progress
Integrating the head (LED only)
Dec 1–15 · Bhavishya · Harsh · Sravan
In progress
Real robot movement testing
Dec 1–15 · Aditya · Thejasvi
Not started
End-to-end integration
Dec 16–31 · All team
Not started
Head with camera (optional)
Dec 16–31 · Harsh · Sravan · Bhavishya
Not started
Our next step
simulation → real robot
1
RL finds the best 6 gait numbers
2
Check them in the simulator
3
Put them + turning into the ESP32 firmware
4
Test walking & turning on the real robot
Notes: Phase four brings everything together. The Jetson Nano and camera and the LED head are already in progress. Next comes testing movement on the real robot and the full end-to-end integration. For the movement, our plan is: reinforcement learning finds the best gait numbers, we check them in the simulator, then move them together with the turning logic into the ESP32 firmware and test on the real robot.

## Slide 5
Still ahead
Remaining work until the final presentation in January
thws
Aditya Srivatsa
5
Phase 3 – finish
ROS 2 framework
Aditya · Thejasvi
Not started
Perfect the robot model (XML)
missing parts
Not started
Camera selection & setup
Harsh · Bhavishya · Sravan
Not started
6
Phase 5 – Finalization (Jan)
Final testing & bug fixing
Jan 1–20 · All
Not started
Remote control, head, HRI
Jan 21–30 · All
Not started
Final presentation
Jan 25–30 · All
Not started
Takeaway: the robot already walks, trots and steers in simulation; Phase 4 brings this onto the real hardware.
Notes: What is still ahead: on the software side, the ROS 2 framework, finishing the robot model, and camera selection. In January, final testing, remote control and the head, and the final presentation. In short: the robot already walks, trots and steers in simulation, and phase four brings that onto the real hardware.